## Sheet1
WEEK10 | 10/28-11/3
Name | Role | Task1 | Note | Complete? | Task2 | Note | Complete? | No Task3 this week
Peter Ly | Narrative Director | World Building: Society/Culture | Look at 8.11 GDD |  | Origins/Background Lore | Simple, can be expanded on later
Joseph Rizzuto | Producer/Sr. Developer | Making the project/refamiliarize with engine |  |  | Make Basic 2P Controls | Use placeholders for now
Daniel Wood | Art/Creative Director | Arena Ring/Stage Modeling | Don't model crowd/audience yet |  | Find reference images | Go online to find these
WEEK11 | 11/4-11/10
Name | Role | Task1 | Note | Complete? | Task2 | Note | Complete? | No Task3 this week
Peter Ly | Narrative Director/Jr. Developer |  |  | Cancelled | Help Joseph with fighting logic if needed
Joseph Rizzuto | Producer/Sr. Developer | Health Bars | Functionality to lower it to achieve 'win state' |  | Fighting Logic (Session 1) | Program when attack moves do damage, stunned state, etc.
Daniel Wood | Art Director | Character modeling for sword fighters | Players differentiated by color for now |  | Animations for slice, dodge, punch, and deflect | Use Mixamo if needed, adhere to 9.5 GDD (MAY BE MOVED LATER IN PLAN)
WEEK12 | 11/11-11/17
Name | Role | Task1 | Note | Complete? | Task2 | Note | Complete? | Task3 | Note | Complete?
Peter Ly | Narrative Director | Brainstorm ideas for assets that can flesh out world | Can be things like posters, ads (made-up products), Jumbo-tron, etc. | Cancelled | Brainstorm ideas for assets that can flesh out world | Can be things like posters, ads (made-up products), Jumbo-tron, etc. | Cancelled | Find SFX and Music | This is up to director's discretion
Joseph Rizzuto | Producer/Sr. Developer | Fighting Logic (Session 2)
Daniel Wood | Art Director | Find different character models | Refer to 6.1 in GDD for character design attributes
WEEK13 | 11/18-11/25
Name | Role | Task1 | Note | Complete? | Task2 | Note | Complete? | Task3 | Note | Complete?
Peter Ly | Jr. Developer | Create different scenes for locker room, arena, title screen, etc. |  |  | Implement SFX |  | WIP | Find voice lines for basic actions (i.e. "TKO!"; "Winner!"; etc.)
Joseph Rizzuto | Producer/Sr. Developer | Asset Importation I, Stamina | Animations + timings are key for importation |  | Implement UI and Scene Navigation |  | WIP
Daniel Wood | Art/Creative Director | Model glove and sword | Items will be attached within engine |  | Logo Design
WEEK14 | 11/11-11/17
Name | Role | Task1 | Note | Complete? | Task2 | Note | Complete? | Task3 | Note | Complete?
Peter Ly | Jr. Developer | Implement announcer voice lines SFX (*and subtitles?) | *OPTIONAL |  | Backstory text for each of the 3 characters, gives them more personality | Can be cut if needed, but it feeds into world-building >> refer to past work (Week 10) |  | Asset importation II (assist others as needed)
Joseph Rizzuto | Producer/Sr. Developer | Adjust fighting logic, physics, and hitboxes as needed. Balancing. |  | WIP | Catch up on previous tasks if needed |  |  | Publish game (??), asset importation II | Specific date TBD
Daniel Wood | Art Director | Create interior of arena (simple 3D or 2D*) and locker room (2D BG) | *Choice depends on time |  | Model low-poly crowd (3-5 copy/paste models) or 2D Sprites | Depends on time |  | Asset Importation II to replace last placeholders | If needed, refer to Joseph for help
This plan is subject to change.