## Sheet1
WEEK10 | 10/28-11/3
Name | Role | Task1 | Note | Complete? | Task2 | Note | Complete? | No Task3 this week
Peter Ly | Narrative Director | World Building: Society/Culture | Look at 8.11 GDD |  | Origins/Background Lore | Simple, can be expanded on later
Joseph Rizzuto | Producer/Sr. Developer | Making the project/refamiliarize with engine |  |  | Make Basic 2P Controls | Use placeholders for now
Daniel Wood | Art Director | Arena Ring/Stage Modeling | Don't model crowd/audience yet | WIP | Find reference images | Go online to find these
WEEK11 | 11/4-11/10
Name | Role | Task1 | Note | Complete? | Task2 | Note | Complete? | No Task3 this week
Peter Ly | Narrative Director/Jr. Developer | Announcer voice lines/dialouge (Session 1) | Refer to 6.2.2 (NPCs) for narration guide | WIP | Help Joseph with fighting logic if needed |  | WIP
Joseph Rizzuto | Producer/Sr. Developer | Health Bars | Functionality to lower it to achieve 'win state' |  | Fighting Logic (Session 1) | Program when attack moves do damage, stunned state, etc. | WIP
Daniel Wood | Art Director | Character modeling for sword fighters | Players differentiated by color for now |  | Animations for slice, dodge, punch, and deflect | Use Mixamo if needed, adhere to 9.5 GDD (MAY BE MOVED LATER IN PLAN)
WEEK12 | 11/11-11/17
Name | Role | Task1 | Note | Complete? | Task2 | Note | Complete? | Task3 | Note | Complete?
Peter Ly | Narrative Director | Announcer voice lines/dialouge (Session 2) | Finish most/all of the lines by this date |  | Brainstorm ideas for assets that can flesh out world | Can be things like posters, ads (made-up products), Jumbo-tron, etc. |  | Add other narratively driven assets | This is up to director's discretion
Joseph Rizzuto | Producer/Sr. Developer | Fighting Logic (Session 2) and Timer | Borrow code from other projects with a timer |  | Implement Placeholder UI (later replaced by Daniel) | Refer to 9.2 GDD for interface assets
Daniel Wood | Art Director | Make hats and different skin tones for fighter characters | Refer to 6.1 in GDD for character design attributes |  | UI Design Stylistics | Change colors, size, position, and look of UI in-game
WEEK13 | 11/11-11/17
Name | Role | Task1 | Note | Complete? | Task2 | Note | Complete? | Task3 | Note | Complete?
Peter Ly | Jr. Developer | Create different scenes for locker room, arena, title screen, etc. | Work with Joseph on this step |  | Split screen functionality (two different cameras) | This can be implemented earlier, if applicable
Joseph Rizzuto | Producer/Sr. Developer | Adjust bounds of each scene and add buttons to swap scenes | Work with Peter on this step |  | Help Peter with his Task2 | Other tasks: TBD |  | Coordinate with Daniel to implement SFX
Daniel Wood | Art Director | Model glove and sword | Items will be attached within engine |  | Touch up title screen UI and other overall UI | Incoporate UI Stylistics |  | Finding BGM and cartoonish SFX
WEEK14 | 11/11-11/17
Name | Role | Task1 | Note | Complete? | Task2 | Note | Complete? | Task3 | Note | Complete?
Peter Ly | Jr. Developer | Make locker room customization scene (if not already done) |  |  | TBD |  |  | Assist Daniel with asset importation
Joseph Rizzuto | Producer/Sr. Developer | Adjust fighting logic, physics, and hitboxes as needed. Balancing. | Other |  | TBD |  |  | Publish game (??), asset importation | Specific date TBD
Daniel Wood | Art Director | Create interior of arena and locker room (scope: simple) | Look at photos for reference but can be simple |  | Model low-poly crowd people (people will be copy-pasted in stands) | Addendum: Differentiate people in crowd (2-3 different skin tones?) |  | Asset Importation to Unity to replace placeholders | If needed, refer to Joseph for help
This plan is subject to change.